## Budget_424c
LWCF Grant Budget Narrative
Project Name: | Harbor Park Improvements
Sponsor: | City of Snowed In, Alaska
Total Project Cost: | 318187.776 | EXAMPLE |  | State Indirect Rate | 8.8%
Federal Share Grant Request: | 159093.888 |  |  | Date Prepared: | 2018-04-05
Scope of Work: Replace restroom facility at Harbor Park, including demolition, construction of new facility with all new fixtures and utilities.
PROPOSED WORK: Numbers and categories correspond to categories on the Standard Form 424c. Add or delete categories as needed. | LWCF grant (federal share) | MATCH - from grant sponsor | MATCH - not from grant sponsor | SUBTOTALS by Category | Pre- Agreement Cost?
4. Architectural and Engineering Fees |  |  |  | 55158
Bidding Assistance |  | 3150
Project Manager (12 weeks x 8hr/wk) |  | 4488
Project expediter (10 weeks x 8hr/wk) |  | 3520
Project Supervisor (10 weeks x 50hr/wk) |  | 44000
5. Other Arc & Engineering Fees |  |  |  | 8408
City Admin/Project Management |  | 8408
8. Demolition and removal |  | 18500 |  | 18500
Demolish interior walls, inside/outside skin of
exterior walls, roof (salvage trusses), and all
interior furnishings
9. Construction (labor contract) * |  |  |  | 77500
Construct new restroom on existing foundation | 30000 | 47500
10. Equipment & Materials (no labor) |  |  |  | 115120
Concrete, masonry, metals, lumber, plastic, thermal and moisture protection, doors and windows, metal roofing, pre-manufactured trusses, gutters, mechanical and electrical equipment, urinals, toilets, basins, stall dividers, grab bars, toilet paper holders, soap dispensers, etc | 100000 | 5000
Forklift: 10 weeks | 1980 | 1980
Flatbed: 10 weeks | 1980 | 1980
Boom Truck: 10 weeks | 1100 | 1100
11. Miscellaneous |  |  |  | 5600
1% for Art | 1000 | 2100
surface freight: 20 tons of materials from seattle | 2500
13. Contingencies |  |  |  | 12166
| 7666 | 4500
Total Direct Costs | 146226 | 146226 |  | 292452
State Indirect Cost (Total direct x 8.8%) | 25735.776 |  |  | 25735.776
Total Project Cost (federal + local + State Indirect) | 318187.776 |  |  | 318187.776
LWCF 50% Federal Share | 159093.888
Potential Reimbursement to Subgrantee (Federal Share - State Indirect) | 133358.112
Over Match:
Notes:
The indirect cost rate in effect will be applied to each billing.
Cost estimates prepared by: Earnest Engineering for the City of Snowed In
Cost categories should align with SF-424c categories. Common categories for LWCF projects are included above; add others as needed to complete the budget detail.
Note on E8: Once this form is complete, put the subtotals in this column in the corresponding categories on the SF-424c. The SF-424c does not include a line for indirect costs. Record that on the SF-424a.