## Snow Den
Milestones
Sponsor: | City of Snow Den
Project Name: | Polar Park
LWCF Project Number: | pending |  | Date: | 2018-11-02
Grant Scope and Purpose: | Rehab and upgrade the children's playground at Polar Park.
Proposed Accomplishments | Proposed Timeframe | Actual Timeframe | Briefly explain difference, if any | Percent Complete
Execute Grant Agreement | May 2019
Order & Deliver Play Equipment | May - June 2019
Site prep, grading, swale & beehive drain | June - July 2019
Asphalt paving, footings, walkway, ramps | July - Aug 2019
Install play equipment, posts, fencing, gate, amenities | Aug - Sept 2019
Finish landscaping of project. Open to public. | May - June 2020
Submit final reimbursement request, 6(f) boundary map, and other required documents to close out grant project. | August 2020

## Other Example
Milestones | Target Date
Initiate Design | 2017-10-01
Apply for Permits | 2017-12-01
60 % Plans Complete | 2018-03-15
NEPA and Section 106 Complete | 2018-05-01
Create Bid Documents & Advertise | 2018-05-15
Submit progress report to State | 2018-07-01
Bids awarded / Contractor Hired | 2018-09-15
Begin Construction | 2019-05-01
50% Construction Complete | 2019-07-01
90% Construction Complete | 2019-08-15
Inspection and Construction Complete | 2019-09-10
Open to the Public | 2019-09-15
Final Billing and Grant Closure | 2019-10-30
Example