## Snow Den_Example
Project Timeframe & Milestones
Sponsor: | City of Snow Den
Project Name: | Polar Park | Date: | 2026-09-30
LWCF Project Number: | pending
Grant Scope and Purpose: | Rehab and upgrade the children's playground at Polar Park.
Proposed Accomplishments | Proposed Timeframe
Execute Grant Agreement | April 2024
Order & Deliver Play Equipment | May - June 2024
Site prep, grading, swale & beehive drain | June - July 2024
Asphalt paving, footings, walkway, ramps | July - Aug 2024
Install play equipment, posts, fencing, gate, amenities | Aug - Sept 2024
Finish landscaping of project. Open to public. | June- July 2025
Submit final reimbursement request, LWCF boundary map, and other required documents to close out grant project. | Aug - Sept 2025

## Other Example
Milestones | Target Date
Initiate Design | 2024-10-01
Apply for Permits | 2024-12-01
60 % Plans Complete | 2025-03-15
NEPA and Section 106 Complete | 2025-05-01
Create Bid Documents & Advertise | 2025-05-15
Submit progress report to State | 2025-07-01
Bids awarded / Contractor Hired | 2025-09-15
Begin Construction | 2026-05-01
50% Construction Complete | 2026-07-01
90% Construction Complete | 2026-08-15
Inspection and Construction Complete | 2026-09-10
Open to the Public | 2026-09-15
Final Billing and Grant Closure | 2026-10-30
Example