## BudgetExample_aligning424c
LWCF Grant Budget Table
Project Name: | Noble Park Improvements
Sponsor: | Snowball Borough
Total Project Cost: | 225120 | EXAMPLE |  | Indirect Rate | n/a
Federal Share Grant Request: | 112560 |  |  | Date Prepared: | 2024-08-01
Scope of Work: Replace restroom facility at Noble Park, including demolition, and new construction of facility with all new fixtures and utilities.
PROPOSED WORK: Numbers and categories correspond to categories on the Standard Form 424c. Add or delete categories as needed. | LWCF Grant (Federal Share) | MATCH from Local Sponsor | MATCH not from Local Sponsor | SUBTOTALS by Category | Pre- Agreement Cost?
4. Architectural and Engineering Fees |  |  |  | 11158
Bidding Assistance |  | 3150
Project Manager (12 weeks x 8hr/wk) |  | 4488
Project expediter (10 weeks x 8hr/wk) |  | 3520
5. Other Arc & Engineering Fees |  |  |  | 8408
City Admin/Project Management |  | 8408
8. Demolition and removal |  | 18500 |  | 18500
Demolish interior walls, inside/outside skin of
exterior walls, roof (salvage trusses), and all
interior furnishings
9. Construction (labor contract) * |  |  |  | 72500
Construct new restroom on existing foundation | 25000 | 47500
10. Equipment & Materials (no labor) |  |  |  | 99993
Concrete, masonry, metals, lumber, plastic, thermal and moisture protection, doors and windows, metal roofing, pre-manufactured trusses, gutters, mechanical and electrical equipment, urinals, toilets, basins, stall dividers, grab bars, toilet paper holders, soap dispensers, etc | 80000 | 9873
Forklift: 10 weeks | 1980 | 1980
Flatbed: 10 weeks | 1980 | 1980
Boom Truck: 10 weeks | 1100 | 1100
11. Miscellaneous |  |  |  | 7311
Surface freight: 20 tons of materials from Seattle |  | 7311
13. Contingencies |  |  |  | 7250
10% of Construction labor estimate. | 2500 | 4750
Total Direct Costs | 112560 | 112560 |  | 225120
Indirect Cost | 0 | 0
Cost Per Federal & Local Sponsor | 112560 | 112560
Total Project Cost (federal + local + indirect) | 225120 |  |  | 225120
Notes: Snowball Borough requires 10-15% contingency to accoutn for escalating costs of materials, labor, or shipping, especially since estimated costs are researched and budgets are often created many months prior to actual purchase and shipping or materials, or prior to actual construction being performed.
Cost estimates prepared by: Snowball Planning Department
Cost categories should align with SF-424c categories. Common categories for LWCF projects are included above; add others as needed to complete the budget detail.
Note on E8: Once this form is complete, put the subtotals in this column in the corresponding categories on the SF-424c. If budgeting indirect costs, record that on Line 1 of the SF-424c.